## Sheet1
Work Division (Group III)
Task: | Person in charge: | Start date: | Finish date: | Completion Percentage/Status: | Member/s who contributed: | Contribution Percentage:
Documentation:
Trello Board Creation | Paulo Kloster | 2022-09-29 |  | 7% | Paulo Kloster
Marvin Coronel
Rocelle Valdez
Keeping records(screenshots for Teams, Trello and Github)
Work Division | Rocelle Valdez | 2022-09-30 |  | 1% | Marvin Coronel
Paulo Kloster
Rocelle Valdez
VMS Flow Charts | Marvin Coronel | 2022-09-29 | 2022-09-30 | 100% | Marvin Coronel
Communication Plan
Project Scope Statement
Gantt Chart
Resource allocation & Cost Estimation
Work Breakdown Structure
Identifying Software Specifications
Creating Project Goals and Meeting Agenda
Steps/Guides for the flowchart | Paulo Kloster | 2022-10-06
Meeting Minutes:
First meeting minutes
Second meeting minutes
Third meeting minutes
Fourth meeting minutes
Fifth meeting minutes
Design:
Paper Sketch *optional
Creating Prototype (using Figma) | Paulo Kloster | 2022-10-02
Creating Database Schema
User Interface Design:
Visitor starting page
Visitor registration page
Company policy page
Log-in page
Dashboard
Admin/Staff page
Implementation(coding):
Log-in page
Admin/Staff page
Data Storage
Starting page
Registration page
Company policy page(legal signing)
Database
Weekly report/dashboard
Testing: