## Sheet1
Work Division (Group III)
Task: | Person in charge: | Start date: | Finish date: | Completion Percentage/Status: | Member/s who contributed: | Contribution Percentage:
VMS Visitor Flow Chart | Marvin Coronel | 2022-09-29 | 2022-09-30 | 100% | Marvin Coronel
Trello Board Creation | Paulo Kloster | 2022-09-29 |  | 0% | Paulo Kloster
Work Division | Rocelle Valdez | 2022-09-30 |  | 1%
Paulo Kloster/ Rocelle/ Marvin
0%
0%
0%
0%
0%